## Sheet1
Location | Date | Minutes | Attendance | Items Discussed | Progress Updates | Agreed Actions
Computer Science Building - A32 Lab | 2025-01-30 | 95 | Meet Patel, Ernestas Kaziulis, Kaliza Gbonda, Yuheng Sheng, Dhanya Kumari Nallakandi | Team introductions , Strengths and weaknesses , Initial game ideas , Setting up Github , Jira , Team and Whatsapp. Discuss team management plans | Team discussions and planning has begun | Download same version of Unity , Join teams,jira and github
Exchange Building - C4 | 2025-02-04 | 30 | Meet Patel, Ernestas Kaziulis, Kaliza Gbonda, Yuheng Sheng, Dhanya Kumari Nallakandi | Jira basics for people in team who havent used it before. Planning Sprint 1 and assigning points to task based on time it will take and assigning task to each team member Getting delivarables ready for Lab1 | Accounts for Github,Jira,Teams and Whatsapp have been sorted , Initial ideas and team personality disccused | Setup Github with Unity Project Files , Documentation for Game Ideas, Sketches,Mechanics and Git usage.
Computer Science Building - A32 Lab | 2025-02-06 | 100 | Meet Patel, Ernestas Kaziulis, Kaliza Gbonda, Yuheng Sheng, Dhanya Kumari Nallakandi, Muhammed Saim Gulay | Quick team stand up discussing sprint tasks. Presented in lab our so far completed tasks and graded 70% | Assigned Project tasks update, presented sprint 1 in lab | Agreed on 70% for the first lab demo, Plan to have MVP (Minimum Viable Product) for next lab demo (move from backlog to active sprint)
Jubliee Conference Centre Auditorium - Workshop | 2025-02-10 | 50 | Ernestas Kaziulis, Kaliza Gbonda, Yuheng Sheng, Dhanya Kumari Nallakandi | Team Workshop about Sprint Retrospectives (what went well, what went bad) and planning poker/ points poker; deciding as a team the estimated time for a task to be completed using poker points | Further knowledge of points poker improved, Quick stand up of current sprint tasks and idea what to have prepared for next lab | Prepared for sprint review on 11/02/2025
Exchange Building - C4 | 2025-02-11 | 90 | Ernestas Kaziulis, Kaliza Gbonda, Yuheng Sheng, Dhanya Kumari Nallakandi (online), Muhammed Saim Gulay | Stand up to go over sprint 1 tasks and complete a sprint retrospective. Planned for upcoming sprint 2, assigned tasks to each team member and planning poker to estimate expected task time. | Prototype being developed, User Stories and Stakeholders been considered, Initial ideas, Git use and Game mechanics documented, MVP plan completed | Tasks assigned on Jira. Develop necessary designs, Progress prototype, Organise team files and Centralise to GitHub Repo, Plan potential questions